## Roles and Responsibilities
Potential Roles and Responsibilities in Data Access and Quality (DAQ) Team
Role | Responsibilities
DAQ Leads | -Project management type of position and coordination with a focus on interagency & interdisciplinary collaboration and inclusion. -Responsible for overall diretion of the DAQ, coordinating across worklanes, translating ICPI priorities into strategic direction for the group, and providing overall leadership and responsibility. -Collaborates with worklane leads to coordinate projects across worklanes and ensure that teams are on track to reach milestones and deliverables. -Serves as the primary point of contact for liaising with ICPI leads, OGAC points of contact, other ICPI clusters, and the PRIME HIS (systems) team. -Responsible for keeping DAQ members up-to-date on systems changes, progress on DAQ projects, and other relevant information through ICPI inbriefs, DAQ meetings, Github, emails, etc.
Worklane Lead | -Coordinates projects within a worklane and delgates specific assignments to analysts/SMEs. May also delegate and designate to individuals on the team to act as project leads for specific projects. May complete project/product work themselves as necessary. -Responsible for keeping timelines, ensuring team is on track to reach milestones, deliverables, and reporting out to DAQ leads about progress on projects. -Responsible for ensuring that staff have performed appropriate and sufficient quality assurance checks (QCs) on all products prior to dissemination. -Coordinates with DAQ leads and other worklane leads to ensure that DAQ priorities are being translated into products and projects
Project Lead | -Takes on the primary responsibility for a larger project or product. This could either be a one-time project/product (such as fulfilling a TDY request to help improve a field team's data management processes) or a product that produced at regularly scheduled intervals (such as the Data Review Tool). -Takes over the primary responsibility for the day-to-day management of timelines, milestones, QCing, and deliverables for their specific project from the worklane lead. Becomes responsible for reporting out to worklane lead on progress for that product. -May perform some aspects of technical work themselves and delegate additional technical work to others assigned to work on the project as necssary.
Analyst or SME | Analysts and SMEs may contribute to the DAQ in a variety of ways which could include acitivites such as: -Providing analytic, technical area, or data stream expertise and ensures that products are appropriate & meet the needs of end users. Provides substantial input on the features or structures of products during the product development phase & engages in end user experience testing. -Creating a product/output and has expertise in data structures or analytic software. -Participating in or leading quality assurance checks (QC) to ensure the accuracy of products prior to release. -Creating documentation, users guides, or training materials for products. -Engaging in capacity building and training of other members of the PEPFAR community through webinars, brown bags, training events, or TDYs. -Fulfilling ad hoc requests for a dataset or product from ECTs, field teams, agency HQ staff, or other ICPI clusters.
Collaborator/ Observer/ Liaison | -Individuals who are a part of the group in a more peripheral role. These individuals stay up to date on the activities of the DAQ, may share DAQ/systems updates with their primary agencies or clusters, and may provide occassional feedback/input on DAQ products or plans.

## Membership
DAQ Membership and Roles Please: 1) confirm your membership in the DAQ 2) list approximate LOEs that you'd be able to contribute to the DAQ 3) Check whether you are interested in being a project lead, Anlyst/SME, or Collaborator 4) Check which worklanes/types of activities you're interested in participating in
First | Agency | Email address | Confirmed Cluster Member | LOE in ICPI | LOE on Cluster | DAQ Lead | Worklane Lead | Project Lead | Analyst or SME | Collaborator/ Observer/Liaison | Data Access & Management | Data Quality | Data Alignment & Integration | Field Engagement | Communication/ Training
Abdul-Wakil, Aliyah | CDC | odc3@cdc.gov |  | 85%
Abellera, JP | CDC
Agedew, Abraham | CDC | lqe1@cdc.gov | X | 100% |  | X | X |  |  |  | X | X | X | X | X
Ahmed, Shazad | CDC | lqa9@cdc.gov |  | 100%
Bale, Jeffrey | CDC | wol3@cdc.gov |  | 5%
Boccanera, Rodrigo | HRSA
Brown, Jess | State
Buehler, Jacob | USAID
Buttolph, Jasmine | Peace Corps
Chafetz, Aaron | USAID
Davis, Josh (ICPI Lead) | USAID |  | X |  |  |  | X
Fitzmaurice, Arthur | CDC | kya2@cdc.gov |  | 50%
Godbole, Ramona | USAID
Hess, Stephanie | DoD | stephanie.a.hess3.ctr@mail.mil
Houston, James C. | CDC | vie3@cdc.gov
Knutson, Audrey | CDC
Lim, Travis | CDC | wvp3@cdc.gov
Mehta, Shaylee | DoD | shaylee.p.mehta.ctr@mail.mil
Mishra, Anubhuti | CDC | nme1@cdc.gov |  | 75%
Mujawar, Mohammed | CDC | lrz5@cdc.gov |  | 75%
Parent, Gregory | CDC
Roha, Kristin | State |  | X |  |  |  | X
Schlenker, Kristy | USAID | kschlenker@usaid.gov | X |  |  | X | X |  |  |  | X | X | X | X | X
Thomas, Anne | DOD
Turkewitz, Couper | DOD | cturkewitz@hivresearch.org
Vinayak, Pooja | State
Would you be willing to be a project lead at some point? (You can be participate both as a potential project lead & an Analyst/SME)
Best estimate of weekly contribution of how much time you would be able to spend on DAQ work

## Draft Activities
Activities | Collaborators | Timeline | Additional Notes
Training
HQ Training on MER Structured Datasets |  | FY18 Q2 - Q3
Field Training on MER Structured Datasets |  | FY18 Q2 - Q3
Collaborate with SIMS Cluster to provide field & HQ training on SIMS Structured Datasets | SIMS Cluster | End of FY18 Q2
ICPI training on data management and processing best practices (using open source platforms) to be done in collaboration with DIV (e.g., R training) | DIV | FY18 Q3
Develop methods & best practices for structuring external data sources in order to facilitate aligning disjointed data sources in Panorama's Analytic Workspaces | DIV | TBD
DRT Training for HQ & Field |  | FY18 Q2
Field Engagement
Develop a menu of specific sample activities that the DAQ could collaborate with field teams on. Share this list via SI Advisors, SI Liaisons, and the Huddle Board in order to create demand |  | FY18 Q2
Develop data management, processing, and repository solutions for generating integrated datasets (including MOH, partner, agency, etc.) for better analysis at different geographical hierarchies (e.g., South Africa district profiles). | Field teams | As requested
Collaborating with field teams to review, improve, streamline data management processes throughout the data lifecycle (i.e. from data collection to data analysis). | Field teams | As requested
Work with field teams to explore innovative or open source technologies to improve data management, access, analysis, etc. | Field teams | As requested
Data Access & Management
Generation & distribution of MER Structured Datasets | Systems Team | FY18 Q1-Q3 | Transition fully to HIS Systems team in Q3
Perform extensive data validatoin and consistency checks across multiple data systems | Systems Team | FY18 Q1-Q2 | Will be the first activity to be fully transitioned in Q2
Documentation (including Release Notes and Data Dictionary) for MER Structured Datasets | Systems Team | FY18 Q1-Q3 | Transition fully to HIS Systems team in Q3
Ongoing maintenance of SQL scripts that are used to generate the MER Structured Datasets | Systems Team | FY18 Q1-Q3 | Transition fully to HIS Systems team in Q3
Generating new derived data elements, calculated indicators, and special features (e.g., MCAD) | Systems Team | FY18 Q1-Q3 | Transition fully to HIS Systems team in Q3
Provide support for Site x IM Genie extract | Systems Team | FY18 Q1-Q3
Fully transition current data management and data processing tasks to PRIME HIS (systems team) | Systems Team | FY18 Q3
Collaborate with systems team to develop and requirements for new systems improvements based on feedback from SMEs (e.g., new calculated indicators, integrated data parameters across data streams) | Systems Team & Analytic Clusters | Ongoing
Analyzing the potential downstream implications of systems changes and ensuring that processes and products are mitigated properly | Systems Team & Analytic Clusters | Ongoing
Advocate for analytical datasets by organization hierachy i.e. OU by IM, PSNU by IM extracts to be deployed in Genie | Systems Team | FY18 Q3-Q4
Creation and dissemination of SIMS Structured Datasets | SIMS | FY18 Q1-Q3
Transition creation of SIMS Structured Datasets to systems team & provide continued input on improvements (e.g., calculated variables, enhancements to dataset structure) | SIMS, Systems Team | FY18 Q4
Generation of annual structured budget dataset | Financial Cluster | FY18 Q4
Ad-hoc data access, management and processing requests |  | Ongoing
Explore innovative data management, processing and visualization methods using open source platforms including R-Shiny, Tableau | DIV | Ongoing
Develop data manuipulation and processing scripts using stats packages |  | Ongoing
Data Quality
Launch DRT in Genie | Systems Team | FY18 Q2
Incorporate additional data cleaning validations into DRT | PRIME, Analytic Clusters, Systems Team | FY18 Q3 - FY18 Q4
Serve as the primary point of contact within ICPI that would collect and collate suggested DATIM favorites for data cleaning & analysis from ICPI clusters which can be proposed to PRIME for inclusion in their new group of officially curated and managed favorites. This is akin to the way that the DIV BI Group has a process to propose improvements for Panorama | PRIME | Ongoing
Liaise with systems team to develop validation reports that can be run at the data entry phase | Systems Team | Long Term
Communication & Liaising
Participates in and provides ICPI representation and input to the DATIM Change Control Board (CCB) | Systems Team | Ongoing
Takes part in PRIME HIS deployment plans - staying up-to-date on the status of various projects and participating as required | Systems Team | Ongoing
Participates in weekly meetings with PRIME HIS (systems team) to discuss systems issues, updates, and improvements for the PEPFAR Datahub, DATIM, and Panorama | Systems Team | Ongoing
Keeps ICPI and agency HQ staff informed about systems updates, changes, and improvements via the weekly ICPI inbrief, emails, and other methods |  | Ongoing

## Draft SOW
DAQ Scope of Work (DRAFT)
Purpose
The primary purpose of the Data Access & Quality (DAQ) Subcommittee is to enable PEPFAR Community and ICPI members with a timely access to PEPFAR data and maximize the use of quality data. The DAQ includes a programmatic and technical focus to:
Identify best practices for data use
Support in the development and requirements setting for improved analytic dataset and data review process across multiple PEPFAR data sources
Create improved data access procedures by creating guidelines and standards with focused consideration to frequency of accessibility, usability and learnability of output
Serve as the link between data users and data systems through the participation in development of the PEPFAR Data Hub, data subsystems (e.g., data visualization and mapping) and Change Control Board
Responsibilities
To fulfill this purpose, the DAQ serves as ICPI’s lead instrument for instituting and managing the following elements of data access and quality as they pertain to the ICPI and the PEPFAR Data Community:
ICPI Leadership Support: Regularly reports to ICPI Leadership about subcommittee activities, coordinates resolutions linked between data use and PEPFAR data systems requiring their support, and to ensure resolutions are communicatedusing the appropriate channels.
Data Management and Integration: Advocates for and helps provide appropriate technology solutions for data access and management for use by ICPI members and PEPFAR Data Community, including:
Suggesting updates to existing technology solutions, such as DATIM.org, the DATIM Genie, Panorama, and PEPFAR Data Hub(PDH)
Leveraging SQL and database expertise to export and provide large data files not obtainable via DATIM, Genie, FACTS Info, or Panorama
Aligning disjointed data structure by defining data architecture and varying data syntax for identifying data commonality between various data streams (i.e. geographical hierarchy, implementation mechanisms, reporting periods, data elements, etc.).
Identify complex data linkages; mapping between data streams and data element definitions; producing calculated indicators and generating integrated data parameters across data streams.
Exporting, structuring, disseminating, and providing appropriate analytical datasets for use
Data Documentation: Takes lead in developing and maintaining data dictionaries, release notes, data lineage diagrams, metadata catalogues, and other documentation for all PEPFAR data sources necessary for responsible data analysis.
Data Use Best Practices: Provides education related to OGAC policies to guide the appropriate use, validation, access, storage, and distribution of PEPFAR data by the ICPI and PEPFAR Community, and works with ICPI Leadership to develop and disseminate best practices for data analysis.
Training: Provides training and resources to enable ICPI and PEPFAR Data Community to apply data management best practices in their day-to-day work.
Data Quality Assurance: Takes lead in assessing and documenting the quality of data sources made available for ICPI analysis and, where necessary, identifying data quality issues and coordinating their resolution with all relevant data stewards, including but not limited to PRIME, DATIM/PDH developers, and SI advisors.
Field Engagement: Develop data management, processing, and repository solutions for generating integrated datasets (including MOH, partner, agency, etc.) for better analysis at different geographical hierarchies(i.e. priority subnational unit, DREAMS districts, site level, or focused geographical analysis). The DAQ team collaborates with country teams in identifying data streams of needed and their Data Lifecycles as well as frequency of accessibility and usability (i.e. data warehouse or open data access, dependent upon on technical and policy stakeholder agreements)